## Tabelle1
Task | Org. Est. | Curr. Est. | Effort | Remain | Responsible
Implement classes according to UML-class diagram without virus | 18 | 24 | 24 | 0
Implement the virus with all its math and physiks | 15 | 15 | 10 | 5
Implement the complex and math-heavy methods | 36 | 36 | 2 | 34
Once this all is done, create a scenario builder and make the first test run/Ut's | 45 | 45 | 1.5 | 43.5
Rework all errors and get as close as possible to our desired output | 45 | 45 | 18 | 27
If we got our desired output, we start with implementing the view with the graphical output | 30 | 10 | 10 | 0
If were done with all we wanted and no changes have to be made anymore we start implementing another model to compare ours | 54 | 54 | 0 | 54