## Tabelle1
Task | Org. Est. | Curr. Est. | Effort | Remain | Responsible
Implement classes according to UML-class diagram without virus | 18 | 24 | 22.5 | 1.5
Implement the virus with all its math and physiks | 15 | 15 |  | 15
Implement the complex and math-heavy methods | 36 | 36 |  | 36
Once this all is done, create a scenario builder and make the first test run/Ut's | 45 | 45 |  | 45
Rework all errors and get as close as possible to our desired output | 45 | 45 |  | 45
If we got our desired output, we start with implemnting the rendererarrarereaere | 30 | 30 |  | 30
If were done with all we wanted and no changes have to be made anymore we start implementing another model to compare ours | 54 | 54 |  | 54