## Tabelle1
Task | Org. Est. | Curr. Est. | Effort | Remain | Responsible
Implement calsses according to UML-class diagram without virus | 6 | 6 | 4 | 2
Implement the virus with all ist math and physiks | 5 | 5 |  | 5
Implement the complex and math-heavy methods | 12 | 12 |  | 12
Once this all is done, create a scenario builder and make the first test run/Ut's | 15 | 15 |  | 15
Rework all errors and get as close as possible to our desired output | 15 | 15 |  | 15
If we got our desired output, we start with implemnting the rendererarrarereaere | 10 | 10 |  | 10
If were done with all we wanted and no changes have to be made anymore we start implementing another model to compare ours | 18 | 18 |  | 18